XO Arena

Development Plan

Version 1.0  |  March 2026

Team size: 2–4 developers  |  Delivery: Phased (v1 → v2 → v3)

Status: Draft

# 1. Overview & Approach

This document defines the phased development plan for XO Arena — a full-stack web-based Tic-Tac-Toe game with PvP, PvAI, real-time rooms, accounts, leaderboards, and admin tooling. The plan is structured for a small team of 2–4 developers working across three explicit release phases.

## 1.1 Phased Release Strategy

The project is divided into four releases, each delivering a meaningful, testable increment. Phase 0 establishes a clean, consistent machine baseline before any code is written. All development and testing through v2 runs entirely on a local macOS machine via Docker Compose. Cloud deployment happens once in v3, after the full product is proven locally.

Phase 0 — Machine Preparation - All developer machines cleaned: no conflicting Docker containers, databases, or port conflicts - Git configured with correct identity and verified access to the project repository - All required tools installed at specified versions (Node 20, Docker Desktop, Playwright, k6) - All accounts and credentials set up: Clerk dev, Stripe test, AWS access confirmed - Orchestrator context infrastructure live: living doc, comms channel, daily sync scheduled - Orchestrator sign-off checklist complete for every developer — Phase 0 exit

v1 — Local-First Foundation - Full local development stack running on macOS via Docker Compose - PvAI gameplay: mode selection, game board, all three difficulty levels (Minimax AI backend service) - User authentication (Clerk: email/password + Google + Apple OAuth) - Basic account, stats, and settings screens - Unit and integration test coverage for all v1 components - Local only — no cloud deployment

v2 — PvP, Real-Time & Full Feature Set - PvP with real-time rooms, mountain name assignment, invite links, and spectator mode - Socket.io + Redis adapter running locally via Docker - Leaderboard, game history, log viewer (admin), and AI dashboard screens - All monetisation, notification, and admin features complete - E2E test suite covering all critical paths — run locally against the Docker stack - Local only — no cloud deployment. Full product verified end-to-end before any AWS work begins.

v3 — Cloud Deployment & Production Go-Live - Full AWS infrastructure provisioned: Elastic Beanstalk, RDS, ElastiCache, S3/CloudFront, CloudWatch - GitHub Actions CI/CD pipelines for staging and production - Clerk production instance configured with production OAuth credentials - All v1 + v2 E2E tests re-run against staging environment - Performance and scalability load testing in AWS - Production go-live readiness review and deployment

## 1.2 Team Roles

With a team of 2–4 developers, the following role allocation is recommended. On smaller teams, individuals cover multiple roles.

| Role | Responsibilities | Primary phases |
| --- | --- | --- |
| Orchestrator (1 dev) | Owns the big picture. Maintains cross-cutting context across all workstreams, manages task dependencies, makes architectural decisions, resolves blockers, ensures PRD/TDD/design doc alignment, conducts phase sign-offs, and maintains the living documentation set. | All phases — continuous |
| Frontend (1–2 devs) | React app, all screens, Tailwind tokens, Zustand state, Howler.js sound, responsive layout | All phases |
| Backend (1–2 devs) | Node.js/Express API, Socket.io, AI service, Clerk integration, Prisma/Postgres, Redis | All phases |
| DevOps / infra (0.5 dev) | Docker Compose local stack (v1–v2), AWS provisioning and CI/CD pipelines (v3) | v3 primarily; Docker support in v1–v2 |
| Testing (shared) | Vitest unit/integration tests written alongside code; Playwright E2E suite in v2+ | All phases |

## 1.3 Orchestrator Role — Detail

The Orchestrator is the single person who holds full context across the entire project at all times. On a small team this is critical — without it, frontend and backend decisions drift apart, phase transitions lose context, and blockers go unresolved. The Orchestrator is not a project manager in the traditional sense; they are a senior technical contributor who also owns the coordination layer.

### Ongoing responsibilities

- Context ownership — maintains a living understanding of all active workstreams, what is in progress, what is blocked, and what is coming next. The single source of truth for 'where are we?'

- Dependency management — tracks the hard dependency chain (Section 7.1) and proactively flags when an upstream task is at risk of blocking downstream work.

- Architectural decisions — owns the final call on any technical decision that spans frontend and backend or introduces a new pattern. Documents decisions with rationale so context is not lost.

- Document maintenance — keeps the PRD, TDD, Design Document, and this Development Plan current as decisions evolve. Ensures the team is always building against the latest agreed spec.

- Pull request oversight — reviews all PRs that cross workstream boundaries (e.g. a backend change that affects the frontend API contract, or a schema migration that affects multiple endpoints).

- Phase sign-off — owns the formal sign-off checklist at the end of each phase before the team moves forward.

- Blocker resolution — first point of contact when a developer is stuck. Either resolves directly or escalates quickly. Prevents blockers from sitting unacknowledged.

### Context maintenance practices

- Maintains a short living document (can be a README, Notion page, or similar) updated at least daily during active development: current phase, active tasks per developer, blockers, next decisions needed.

- Runs a brief daily sync (15 minutes maximum) to surface blockers and confirm each developer's next task is unblocked.

- At the end of each sprint or work week, writes a short context snapshot: what was completed, what carried over, any decisions made, any risks that materialised.

- Before any phase transition, produces a written sign-off summary confirming all exit criteria are met and capturing any deferred items for the next phase.

### On a team of 2–4

- The Orchestrator role is additive — this person also contributes code, typically as a backend or full-stack developer. The orchestration work is estimated at 15–20% of their time in active phases.

- On a 2-person team, the Orchestrator is one of the two developers. The cost is real but the alternative — no one owning context — is worse.

- On a 3–4 person team, the Orchestrator is ideally the most experienced developer, with the remaining 80–85% of their time on backend or full-stack tasks.

## 1.4 Conventions

- Every task must have a passing unit test before it is considered complete (per the testing philosophy in TDD Section 11).

- All code is committed to a Git repository. Feature branches merge to main via pull requests with at least one reviewer — the Orchestrator reviews all cross-workstream PRs.

- The pre-commit Husky hook blocks commits with failing unit tests.

- v1 and v2 phases end with a full local sign-off (all tests green, full Docker stack verified) before moving to the next phase. v3 ends with staging and production deployment sign-off. Sign-off is owned by the Orchestrator.

- Effort estimates are in developer-days (1 dev-day = one developer working one full day). They are indicative, not contractual.

- The Orchestrator's living context document and daily sync are non-negotiable — they are the minimum coordination overhead that keeps a small team coherent across a project of this scope.

# 2. Phase 0 — Machine Preparation

Before any code is written, every developer's machine must be in a known-good, clean state. This phase ensures a consistent starting point: stale Docker containers, orphaned databases, conflicting tool versions, and leftover projects from previous work are all removed or isolated. Phase 0 is completed once per developer machine and signed off by the Orchestrator before Phase 0 exit.

## 2.1 Phase 0 Goal & Exit Criteria

- Every developer's Mac has a clean, documented software baseline with no conflicting Docker containers, databases, or tool versions.

- Git is configured with correct identity and SSH/HTTPS credentials verified against the project repository.

- Docker Desktop is running cleanly with no orphaned volumes or containers from other projects that could cause port conflicts.

- All required tools are installed at the specified versions and verified working.

- Each developer has confirmed the machine baseline by running the verification checklist below.

- Orchestrator has signed off on each developer's environment before Phase 0 is considered complete.

## 2.2 Phase 0 Task Breakdown

### 2.2.1 Docker Cleanup

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| M-01 | Stop and remove all running Docker containers unrelated to this project: docker stop $(docker ps -q) && docker rm $(docker ps -aq) | 0.5d | Each dev | Do not remove containers you still need for other active projects — isolate them instead |
| M-02 | Remove orphaned Docker volumes that may conflict: docker volume prune | 0.5d | Each dev | Review before pruning — confirm no volumes needed by other active projects |
| M-03 | Remove unused Docker networks: docker network prune | 0.5d | Each dev |  |
| M-04 | Confirm Docker Desktop is on a supported version (Docker Desktop ≥ 4.25); update if needed | 0.5d | Each dev | Required for Docker Compose v2 syntax |
| M-05 | Verify no port conflicts on the ports this project will use: 5173 (frontend), 3000 (backend), 5432 (Postgres), 6379 (Redis) | 0.5d | Each dev | lsof -i :5173 :3000 :5432 :6379 — kill or reassign any occupying processes |

### 2.2.2 Database Cleanup

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| M-06 | Identify and remove any locally running Postgres instances not needed for other active projects (Homebrew postgres, local pg clusters, etc.) | 0.5d | Each dev | brew services stop postgresql or pg_ctl stop as appropriate |
| M-07 | Identify and remove any locally running Redis instances not needed for other active projects | 0.5d | Each dev | brew services stop redis as appropriate |
| M-08 | Confirm no residual database data directories that could conflict with the project's Dockerised Postgres volume | 0.5d | Each dev | Project DB will live in a named Docker volume — clean slate preferred |

### 2.2.3 Tool Installation & Version Verification

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| M-09 | Install Node.js 20 LTS via nvm: nvm install 20 && nvm use 20 && nvm alias default 20 | 0.5d | Each dev | Verify: node --version → v20.x.x |
| M-10 | Install or update npm to latest: npm install -g npm@latest | 0.5d | Each dev | Verify: npm --version |
| M-11 | Install Git if not present; configure git config --global user.name and user.email | 0.5d | Each dev | Verify: git --version ≥ 2.40 |
| M-12 | Install VS Code (or agreed IDE) with recommended extensions: ESLint, Prettier, Tailwind IntelliSense, Prisma, Docker | 0.5d | Each dev | Extensions list committed to .vscode/extensions.json in repo |
| M-13 | Install Playwright system dependencies for E2E testing (required later in v2): npx playwright install --with-deps | 0.5d | Each dev | Do now to avoid surprises in v2; takes time on first install |
| M-14 | Install k6 load testing tool (required in v3): brew install k6 | 0.5d | Each dev | Install now while setting up; zero cost to have it ready |

### 2.2.4 Git & Repository Setup

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| M-15 | Generate or verify SSH key for GitHub; add public key to GitHub account | 0.5d | Each dev | ssh -T git@github.com should return authenticated confirmation |
| M-16 | Create the project GitHub repository (Orchestrator task): private, with main and staging branches protected | 0.5d | Orchestrator | Branch protection: require PR + passing CI before merge |
| M-17 | Each developer clones the repository and verifies push access with a test commit to a personal branch | 0.5d | Each dev | Confirms Git credentials, SSH, and branch permissions all working |
| M-18 | Configure .gitconfig commit signing (optional but recommended): GPG or SSH commit signing | 0.5d | Each dev | Recommended for a professional project; not blocking |

### 2.2.5 Accounts & Credentials

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| M-19 | Each developer creates or verifies a Clerk development account; Orchestrator creates the shared Clerk development application and distributes dev API keys | 0.5d | Orchestrator + each dev | Keys go into .env file only — never committed |
| M-20 | Orchestrator creates a Stripe test account; distributes Stripe test publishable and secret keys | 0.5d | Orchestrator | Test keys only at this stage |
| M-21 | Each developer verifies AWS CLI is installed and has access to the project AWS account (even if AWS work is v3 — better to confirm access early) | 0.5d | Each dev | aws sts get-caller-identity should succeed; resolve IAM issues now not in v3 |
| M-22 | Document all required environment variables in a shared (password-manager-protected) location; distribute to all developers | 0.5d | Orchestrator | Never in Slack, email, or repo — use 1Password, Bitwarden, or similar |

### 2.2.6 Orchestrator — Context Infrastructure

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| M-23 | Create the living context document (Notion, Confluence, or a CONTEXT.md in the repo): initial state — Phase 0 in progress, developers listed, open questions noted | 0.5d | Orchestrator | This document is updated at the start of every working day |
| M-24 | Set up a project communication channel (Slack, Discord, or similar) with channels: #general, #frontend, #backend, #devops, #blockers | 0.5d | Orchestrator | #blockers is mandatory — all blockers posted here immediately |
| M-25 | Schedule the daily sync (15 minutes, same time each day); confirm all developers have accepted the recurring invite | 0.5d | Orchestrator | Non-negotiable per Section 1.3 |
| M-26 | Produce and distribute Phase 0 sign-off checklist; collect confirmation from each developer that their machine passes all checks | 0.5d | Orchestrator | Phase 0 is not complete until all developers have signed off |

## 2.3 Phase 0 Summary

| Area | Tasks | Est. effort | Done when |
| --- | --- | --- | --- |
| Docker cleanup | 5 | ~2.5d per dev | No port conflicts; no orphaned containers/volumes |
| Database cleanup | 3 | ~1.5d per dev | No local Postgres or Redis conflicting on project ports |
| Tool installation & verification | 6 | ~3d per dev | All tools at specified versions; Playwright + k6 installed |
| Git & repository setup | 4 | ~2d total | All devs have verified push access; branches protected |
| Accounts & credentials | 4 | ~2d total | All API keys distributed securely; AWS access confirmed |
| Orchestrator context infrastructure | 4 | ~2d (Orchestrator) | Living doc live; comms channel active; daily sync scheduled |
| Total (Phase 0) | 26 | ~2–3 days per dev | Orchestrator sign-off checklist complete for all developers |

Phase 0 takes approximately 2–3 days per developer working independently, with the Orchestrator running concurrently on repository, credential, and context setup. It is short but non-negotiable — skipping it means the first time a port conflict or missing tool is discovered is mid-development, not before it starts.

# 3. Prerequisites & Project Scaffolding

These tasks establish the foundational repository structure, Docker Compose local stack, and project scaffolding that all phase-specific development depends on. Phase 0 (machine preparation) must be complete before these tasks begin.

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
|  | Repository & Project Structure |  |  |  |
| P-01 | Create Git repository with monorepo structure: /frontend, /backend, /shared | 0.5d | All | Include .gitignore, README, LICENSE |
| P-02 | Set up GitHub Actions CI skeleton: lint + test on every push | 0.5d | Backend | Add badge to README |
| P-03 | Configure Husky pre-commit hook running Vitest unit suite | 0.5d | Any | Blocks commit on failure |
|  | Local Development Environment |  |  |  |
| P-04 | Author docker-compose.yml: frontend (Vite dev), backend (Node/Nodemon), Postgres, Redis | 1d | Backend/DevOps | docker compose up starts full stack |
| P-05 | Create .env.example with all required environment variable keys documented | 0.5d | Any | No secrets committed to repo |
| P-06 | Verify full local stack starts cleanly on macOS with Docker Desktop | 0.5d | Any | Smoke test: all services healthy |
|  | Tooling & Configuration |  |  |  |
| P-07 | Initialise frontend: Vite + React 18 + TypeScript + Tailwind CSS + design tokens | 1d | Frontend | Implement full color palette and type scale from Design Doc |
| P-08 | Initialise backend: Node.js 20 + Express + TypeScript + Prisma + ESLint + Prettier | 1d | Backend |  |
| P-09 | Configure Vitest for frontend (+ React Testing Library) and backend (+ Supertest) | 0.5d | Any | Test runner confirmed working |
| P-10 | Set up shared TypeScript types package (/shared) for API contracts and game state types | 0.5d | Any | Consumed by both frontend and backend |

Total prerequisite effort: approximately 7 developer-days. These tasks can be parallelised across 2 developers. Phase 0 must be signed off before these begin.

# 4. Phase v1 — Local-First Foundation

Phase v1 delivers a fully playable PvAI game running on a single macOS machine. All core gameplay, authentication, and basic account features are complete by the end of this phase. No cloud deployment is required — the entire stack runs locally via Docker Compose.

## 3.1 v1 Goal & Exit Criteria

- A developer (or tester) can clone the repository, run docker compose up, and play a complete PvAI game at all three difficulty levels within 10 minutes of setup.

- User can register, log in (email/password, Google, Apple), play games, and see their stats.

- All v1 tasks have passing unit and integration tests.

- No known critical bugs in core game flow.

## 3.2 v1 Task Breakdown

### 3.2.1 Database Schema

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| DB-01 | Define Prisma schema: Users, Games, Moves, AI Errors, Stats tables | 1d | Backend | Per TDD Section 6.1 data model |
| DB-02 | Write and run initial Prisma migration on local Postgres | 0.5d | Backend |  |
| DB-03 | Create seed script with sample users and game data for local dev | 0.5d | Backend | Speeds up frontend dev |

### 3.2.2 Authentication (Clerk)

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| AUTH-01 | Create Clerk development instance; configure Google and Apple OAuth providers | 0.5d | Backend | Free Clerk dev account sufficient |
| AUTH-02 | Integrate Clerk frontend SDK into React app: sign-in, sign-up, user button components | 1d | Frontend |  |
| AUTH-03 | Add Clerk JWT verification middleware to Express backend (all protected routes) | 0.5d | Backend |  |
| AUTH-04 | Implement guest mode: unauthenticated users can access PvAI mode only | 0.5d | Frontend/Backend |  |
| AUTH-05 | Write unit tests: JWT middleware, guest access enforcement | 0.5d | Backend |  |

### 3.2.3 AI Service

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| AI-01 | Build AI implementation registry module with common interface (board, difficulty, player) => move | 1d | Backend | Per TDD Section 4.3 |
| AI-02 | Implement Minimax engine: Easy (random), Medium (rule-based), Hard (full Minimax lookahead) | 2d | Backend | All three difficulty levels in one registered implementation |
| AI-03 | Expose GET /api/v1/ai/implementations endpoint returning registry list | 0.5d | Backend | Frontend AI selector reads from this |
| AI-04 | Expose POST /api/v1/ai/move endpoint with implementation selector + board state | 0.5d | Backend | Returns move index + engine ID + duration_ms |
| AI-05 | Write unit tests: Minimax correctness fixtures, all difficulty behaviours, registry routing, 500ms performance assertion | 1.5d | Backend | Per TDD Section 11.3 |
| AI-06 | Write integration tests: POST /api/v1/ai/move round-trip for all difficulties | 0.5d | Backend |  |

### 3.2.4 Core API Endpoints

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| API-01 | POST /api/v1/users — create user profile on first Clerk login (webhook) | 0.5d | Backend |  |
| API-02 | GET/PATCH /api/v1/users/:id — fetch and update user profile | 0.5d | Backend |  |
| API-03 | POST /api/v1/games — create game record on game start | 0.5d | Backend |  |
| API-04 | PATCH /api/v1/games/:id — update game on completion (outcome, moves, duration) | 0.5d | Backend |  |
| API-05 | GET /api/v1/users/:id/stats — return win/loss/draw/streak stats | 0.5d | Backend |  |
| API-06 | POST /api/v1/logs — frontend log ingestion endpoint | 0.5d | Backend | Writes to stdout + log file locally |
| API-07 | Write integration tests for all v1 endpoints | 1d | Backend |  |

### 3.2.5 Frontend — App Shell & Navigation

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| FE-01 | Build app shell: top nav, sidebar, mobile bottom tab nav, responsive breakpoint (768px) | 2d | Frontend | Per Design Doc Section 5 |
| FE-02 | Implement theme toggle (light/dark/system) with CSS variable switching and account persistence | 1d | Frontend |  |
| FE-03 | Set up Zustand stores: auth, preferences (theme, sound), active game | 0.5d | Frontend |  |
| FE-04 | Write component unit tests: shell, nav, theme toggle | 0.5d | Frontend |  |

### 3.2.6 Frontend — Mode Selection Screen

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| FE-05 | Build mode selection screen: PvP/PvAI cards, first-player pills, name fields, CTA | 1d | Frontend | Per Wireframe 1 |
| FE-06 | AI implementation selector: fetch from GET /api/v1/ai/implementations, render radio list | 0.5d | Frontend | Difficulty always requires explicit selection |
| FE-07 | Write unit tests: mode card selection, AI selector population, CTA label adaptation | 0.5d | Frontend |  |

### 3.2.7 Frontend — Game Board (PvAI)

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| FE-08 | Build 3×3 game board component: X/O marks (blue/teal), empty cell hover, win highlight (amber) | 1.5d | Frontend | Per Design Doc Section 4 component specs |
| FE-09 | Implement game state logic: turn management, win/draw detection (all 8 combinations), board locking | 1d | Frontend | Client-side state only for PvAI |
| FE-10 | Integrate AI move API: POST /api/v1/ai/move on each player turn; board dims + spinner during request | 1d | Frontend/Backend | 500ms timeout handling |
| FE-11 | Build turn indicator, score strip (persists across rounds), action buttons (Rematch/New Game/Forfeit) | 1d | Frontend | Forfeit requires confirmation dialog |
| FE-12 | Integrate Howler.js: move sound, win fanfare, draw sound, forfeit sound, mute toggle | 1d | Frontend |  |
| FE-13 | Persist game result via POST/PATCH /api/v1/games on game end | 0.5d | Frontend/Backend |  |
| FE-14 | Write unit tests: win detection, draw detection, turn logic, board locking, score persistence | 1d | Frontend |  |

### 3.2.8 Frontend — Account & Settings Screens

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| FE-15 | Build account/profile screen: profile header, stats grid, win rate bars, streak grid, recent games | 2d | Frontend | Per Wireframe 4; mobile simplified view |
| FE-16 | Build settings screen: theme, sound (master + granular toggles + volume slider), gameplay defaults | 1.5d | Frontend | Per Wireframe 6; persist to account |
| FE-17 | Build settings sub-sections: AI opponent selector, account management (edit profile, sign out, delete) | 1d | Frontend | Delete requires typed confirmation |
| FE-18 | Write unit tests: settings persistence, profile edit, stat display | 0.5d | Frontend |  |

### 3.2.9 Frontend — Log Transport

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| FE-19 | Build frontend log transport module: batches entries, ships to POST /api/v1/logs every 5s (ERROR/FATAL immediate) | 1d | Frontend | Mirror to browser console in dev only |
| FE-20 | Write unit tests: batching logic, retry on failure, immediate dispatch for ERROR/FATAL | 0.5d | Frontend |  |

## 3.3 v1 Summary

| Area | Tasks | Est. effort | Test coverage |
| --- | --- | --- | --- |
| Prerequisites | 10 | 7d | Unit + integration |
| Database schema | 3 | 2d | Integration (Prisma) |
| Authentication | 5 | 3d | Unit + integration |
| AI service | 6 | 6d | Unit + integration + perf |
| Core API endpoints | 7 | 4d | Integration |
| Frontend — shell & nav | 4 | 4d | Unit (component) |
| Frontend — mode selection | 3 | 2d | Unit (component) |
| Frontend — game board (PvAI) | 7 | 7d | Unit (logic + component) |
| Frontend — account & settings | 4 | 5d | Unit (component) |
| Frontend — log transport | 2 | 1.5d | Unit |
| Total (v1) | 51 | ~41.5 dev-days | All v1 units covered |

With 2 developers working in parallel (one frontend-focused, one backend-focused), v1 is achievable in approximately 4–5 weeks.

# 5. Phase v2 — PvP, Real-Time & Full Feature Set

Phase v2 adds real-time Player vs. Player gameplay, all admin screens, and completes the full product feature set — all running locally via Docker Compose. No cloud deployment occurs in this phase. The goal is to have the entire product proven and tested locally before any AWS infrastructure work begins in v3.

## 4.1 v2 Goal & Exit Criteria

- Two players on different browser windows on the local machine can create a room, join via invite link, play a complete PvP game, and have results recorded.

- Spectators can join any room via invite link and watch the game live.

- All admin screens (log viewer, AI dashboard) are functional against the local stack.

- All monetisation and notification features are complete locally.

- All v2 tasks have passing unit, integration, and E2E tests (E2E run against local Docker stack).

- No cloud deployment — local only. All tests pass before v3 begins.

## 4.2 v2 Task Breakdown

### 4.2.1 Real-Time Infrastructure

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| RT-01 | Add Socket.io to Express backend server with Redis adapter (Redis runs locally via Docker Compose) | 1d | Backend | Per TDD Section 5; Redis already in docker-compose.yml from Prerequisites |
| RT-02 | Implement room lifecycle: create, join, spectate, leave, close; mountain name assignment from server-side list (1,000+ names) | 2d | Backend | Name returned to pool on close |
| RT-03 | Implement Socket.io events: move-made, turn-changed, game-ended, forfeit, player-disconnected, spectator-joined/left | 1.5d | Backend |  |
| RT-04 | Implement 60-second reconnection window: hold room state, notify opponent, restore on reconnect | 1d | Backend |  |
| RT-05 | Enforce spectator role server-side: block move/forfeit/rematch events from spectator connections | 0.5d | Backend |  |
| RT-06 | Write integration tests: room lifecycle, reconnection window, spectator role enforcement | 1d | Backend |  |

### 4.2.2 Rooms API

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| API-08 | POST /api/v1/rooms — create room, assign mountain name, return invite URL | 0.5d | Backend |  |
| API-09 | GET /api/v1/rooms/:name — look up room by mountain name | 0.5d | Backend |  |
| API-10 | GET /api/v1/rooms — list active rooms (for join/watch list on desktop) | 0.5d | Backend | Live status, spectator count |
| API-11 | Write integration tests for room API endpoints | 0.5d | Backend |  |

### 4.2.3 Frontend — Room Creation & Join

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| FE-21 | Build room creation screen: settings card (mark, spectator toggle), room name preview with ↻ refresh, invite link copy + share | 1.5d | Frontend | Per Wireframe 3 |
| FE-22 | Build waiting state screen: player slots (filled/waiting), live spectator count, invite link, cancel room | 1d | Frontend |  |
| FE-23 | Build active rooms list (desktop only): join (Waiting) and watch (Live) buttons, spectator count | 1d | Frontend |  |
| FE-24 | Write unit tests: room creation form, waiting state, active rooms list | 0.5d | Frontend |  |

### 4.2.4 Frontend — PvP Game Board

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| FE-25 | Extend game board to support PvP mode: connect to Socket.io room, send/receive move events | 2d | Frontend | Board locks on opponent's turn |
| FE-26 | Add spectator view: amber spectating banner, read-only board, Leave/Start own game actions | 1d | Frontend | Per Wireframe 2 spectator view |
| FE-27 | Show spectator list in right info panel (desktop): names + join times, live count badge | 0.5d | Frontend |  |
| FE-28 | Handle disconnection UX: notify player, show countdown timer for reconnect window | 1d | Frontend |  |
| FE-29 | Write unit tests: PvP turn enforcement, spectator event handling, disconnect notification | 0.5d | Frontend |  |

### 4.2.5 Leaderboard & Game History

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| API-12 | GET /api/v1/leaderboard — global rankings with filters (period, mode) | 1d | Backend | Paginated; aggregated from Games table |
| API-13 | GET /api/v1/users/:id/games — game history with pagination | 0.5d | Backend |  |
| FE-30 | Build leaderboard screen: podium (top 3), my rank callout, filterable table, win rate bar column | 2d | Frontend | Per Wireframe 5; desktop only |
| FE-31 | Build game history screen: full game list with result, opponent, mode, room, date; desktop only | 1d | Frontend |  |
| FE-32 | Write unit + integration tests: leaderboard ranking logic, history pagination | 0.5d | Backend |  |

### 4.2.6 Log Viewer (Admin)

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| LOG-01 | Backend: GET /api/v1/logs endpoint with filters (level, source, userId, sessionId, roomId, time range, search); paginated | 1.5d | Backend | Admin role required |
| LOG-02 | Backend: WebSocket channel for live log tail (new entries streamed to connected admin clients) | 1d | Backend | Auto-pauses when client scrolls up |
| LOG-03 | Frontend: build log viewer screen — filter panel, table with expandable JSON rows, live tail toggle, export (JSON + CSV) | 2.5d | Frontend | Per Wireframe 8; desktop + admin only |
| LOG-04 | Write unit + integration tests: filter logic, pagination, role enforcement | 0.5d | Backend |  |

### 4.2.7 E2E Test Suite (v2 — local)

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| E2E-01 | Set up Playwright project: install, configure for Chromium/Firefox/WebKit, target local Docker stack (localhost:5173) | 1d | Any | Per TDD Section 11.2.3 |
| E2E-02 | Write critical path E2E tests: full PvAI game flow, full PvP game flow (two browser contexts), spectator flow | 2d | Any | Tagged as critical-path |
| E2E-03 | Write E2E tests: user registration (email + Google + Apple OAuth), login, account stats display | 1d | Any |  |
| E2E-04 | Write E2E tests: room creation, invite link, join, mountain name assignment, active rooms list | 1d | Any |  |
| E2E-05 | Write E2E tests: log viewer filter interactions, live tail, export | 0.5d | Any |  |
| E2E-06 | Write E2E tests: AI dashboard filter interactions, chart rendering, CSV export | 1d | Any |  |
| E2E-07 | Write E2E tests: cosmetic shop browse/purchase (mock payment), notifications panel | 1d | Any |  |

### 4.2.8 AI Dashboard

AI dashboard data collection, API, and frontend tasks are included in v2 so the full product is complete locally before cloud deployment.

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
|  | Data collection (schema extensions) |  |  |  |
| AID-01 | Extend Prisma schema: per-move Moves table (game_id, move_number, player, board_state, cell_index, computation_ms, timestamp) | 1d | Backend | Per TDD Section 10.9 |
| AID-02 | Extend Prisma schema: AI Errors table (game_id, implementation_id, error_type, message, stack_trace, timestamp) | 0.5d | Backend |  |
| AID-03 | Update AI move endpoint to write per-move records and errors to new tables | 0.5d | Backend |  |
|  | Backend API |  |  |  |
| AID-04 | GET /api/v1/admin/ai/summary — KPI scorecard with period deltas (Redis-cached 60s TTL) | 1.5d | Backend | Admin role required |
| AID-05 | GET /api/v1/admin/ai/outcomes — outcomes by difficulty chart data | 1d | Backend |  |
| AID-06 | GET /api/v1/admin/ai/move-times — histogram data (p50, p90, p99) | 1d | Backend |  |
| AID-07 | GET /api/v1/admin/ai/win-rate-trend — daily win rate with deployment marker data | 1d | Backend |  |
| AID-08 | GET /api/v1/admin/ai/heatmap — player opening and move frequency heatmap data | 1d | Backend |  |
| AID-09 | GET /api/v1/admin/ai/comparison — implementation comparison table | 0.5d | Backend |  |
| AID-10 | Socket.io channel: stream live AI request volume and move time metrics to dashboard | 1d | Backend |  |
| AID-11 | Write unit + integration tests for all AI dashboard API endpoints | 1.5d | Backend |  |
|  | Frontend |  |  |  |
| AID-12 | Build AI dashboard shell: global filters, live indicator, auto-refresh | 1d | Frontend | Per Wireframe 7 |
| AID-13 | Build KPI scorecard row (6 cards with period deltas) | 0.5d | Frontend |  |
| AID-14 | Build outcomes by difficulty chart (Recharts grouped bar) | 1d | Frontend |  |
| AID-15 | Build move time histogram with p50/p90/p99 markers | 1d | Frontend |  |
| AID-16 | Build win rate over time chart (Recharts line) with deployment markers | 1.5d | Frontend |  |
| AID-17 | Build player opening heatmap (3×3 colour intensity grid) | 1d | Frontend |  |
| AID-18 | Build implementation comparison table with active row highlight and status flags | 1d | Frontend |  |
| AID-19 | Add CSV export button to each chart panel | 0.5d | Frontend | Respects active filters |
| AID-20 | Write unit tests: chart data rendering, filter interactions, export | 1d | Frontend |  |

### 4.2.9 Monetisation

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| MON-01 | Design and implement cosmetic item schema: Items and UserItems tables in Prisma | 1d | Backend | Purely cosmetic, no gameplay impact |
| MON-02 | Integrate Stripe: checkout flow for cosmetic purchases and premium subscription (Stripe test mode locally) | 2d | Backend | Webhook handling for payment events |
| MON-03 | Build cosmetic item shop frontend: browse, purchase flow, apply to game board | 2d | Frontend |  |
| MON-04 | Implement premium subscription tier: ad-free flag, exclusive themes unlocked | 1d | Backend/Frontend |  |
| MON-05 | Implement non-intrusive ads for guest and free-tier users (outside active gameplay only) | 1d | Frontend | No ads during active game |
| MON-06 | Write unit + integration tests for purchase flow and subscription state | 1d | Backend |  |

### 4.2.10 Notifications

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| NOT-01 | Design notification schema: Notifications table in Prisma | 0.5d | Backend |  |
| NOT-02 | In-app notification system: opponent joined, game result, streak milestone; bell icon with unread count | 1.5d | Backend/Frontend |  |
| NOT-03 | Build notifications panel: list, mark read, clear all | 1d | Frontend |  |
| NOT-04 | Email notifications (optional stretch): game result, weekly stats via SendGrid — opt-in only | 1d | Backend |  |

## 4.3 v2 Summary

| Area | Tasks | Est. effort | Test coverage |
| --- | --- | --- | --- |
| Real-time infrastructure | 6 | 7d | Integration |
| Rooms API | 4 | 2d | Integration |
| Frontend — room creation & join | 4 | 4d | Unit |
| Frontend — PvP game board | 5 | 5d | Unit |
| Leaderboard & history | 5 | 5d | Unit + integration |
| Log viewer | 4 | 5.5d | Unit + integration |
| E2E test suite (local) | 7 | 7.5d | E2E (Playwright / local) |
| AI dashboard | 20 | 21d | Unit + integration |
| Monetisation | 6 | 8d | Unit + integration |
| Notifications | 4 | 4d | Unit |
| Total (v2) | 65 | ~69d | Unit + integration + E2E (local) |

With 2–3 developers in parallel, v2 is achievable in approximately 8–10 weeks following v1 sign-off. This phase is larger than v1 as it includes the full feature set. The payoff is that cloud deployment in v3 is unblocked by a fully tested, complete product.

# 6. Phase v3 — Cloud Deployment & Production Go-Live

Phase v3 takes the fully tested, locally verified product and deploys it to AWS. No new features are built in this phase — the focus is entirely on infrastructure provisioning, environment configuration, E2E re-validation against cloud environments, performance hardening, and production go-live. This phase requires v2 to be fully complete with all tests passing locally.

## 5.1 v3 Goal & Exit Criteria

- The complete application is deployed to staging and production on AWS.

- All v1 + v2 E2E tests pass against the staging environment.

- Performance targets met under load testing (AI move endpoint ≤500ms, Socket.io rooms stable under target concurrent load).

- Production go-live readiness review completed and signed off by the team.

- Monitoring, alerting, and log infrastructure operational in production.

## 5.2 v3 Task Breakdown

### 5.2.1 AWS Infrastructure Provisioning

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| OPS-01 | Set up AWS account structure: IAM roles, VPC, security groups, Secrets Manager for all credentials | 1d | DevOps | Principle of least privilege throughout |
| OPS-02 | Provision AWS RDS PostgreSQL (staging + production); run Prisma migrations against each environment | 1d | DevOps |  |
| OPS-03 | Provision AWS ElastiCache Redis (staging + production) for Socket.io Redis adapter | 0.5d | DevOps | Same adapter config as local — no code changes needed |
| OPS-04 | Set up AWS Elastic Beanstalk environments (staging + production) for Node.js backend | 1d | DevOps |  |
| OPS-05 | Set up AWS S3 bucket + CloudFront distribution for frontend (staging + production) | 0.5d | DevOps |  |
| OPS-06 | Configure AWS CloudWatch Logs; update log transport env var to route to CloudWatch in cloud environments (local remains stdout + file) | 1d | DevOps/Backend | Single env var switch — no code changes needed |
| OPS-07 | Configure Clerk production instance; add production OAuth credentials for Google and Apple | 0.5d | Backend | Apple production credentials may take 1–2 days — start early |
| OPS-08 | Configure Stripe production account and webhook endpoints for payment processing | 0.5d | Backend | Switch from Stripe test mode to production keys |

### 5.2.2 CI/CD Pipelines

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| OPS-09 | Build GitHub Actions CI pipeline: lint + unit tests + integration tests on every pull request | 1d | DevOps | Formalises what runs locally; adds cloud gate |
| OPS-10 | Build GitHub Actions staging deploy pipeline: on merge to staging branch → build → deploy to Elastic Beanstalk + S3/CloudFront | 1d | DevOps |  |
| OPS-11 | Build GitHub Actions production deploy pipeline: on merge to main → deploy to production (after staging E2E pass) | 0.5d | DevOps | Requires manual approval gate before production deploy |
| OPS-12 | Configure CloudWatch alarms and SNS alerts: error rate spike, high latency, instance health | 0.5d | DevOps |  |

### 5.2.3 Staging Deployment & E2E Re-validation

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| OPS-13 | Deploy full application to staging environment | 0.5d | All | First cloud deployment — expect some environment-specific config issues |
| OPS-14 | Update Playwright E2E configuration to target staging URL (environment variable switch) | 0.5d | Any | No test rewrites needed — same tests, different target |
| OPS-15 | Run full v1 + v2 E2E suite against staging; resolve any environment-specific failures | 1.5d | All | Allow time for debugging cloud-specific issues |
| OPS-16 | Add E2E pipeline step: full suite runs post-staging deploy; critical-path tests block production promotion | 0.5d | DevOps |  |
| OPS-17 | Staging sign-off: all features verified end-to-end, all E2E tests green | 0.5d | All | Required before production deploy |

### 5.2.4 Performance & Scalability Hardening

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| PERF-01 | Add database indexes: Games(implementation_id, difficulty, started_at), Moves(game_id), Users(username) | 0.5d | Backend | Supports AI dashboard query performance at scale |
| PERF-02 | Verify Redis caching is operational in cloud: AI dashboard metrics (60s TTL), leaderboard queries (5min TTL) | 0.5d | Backend | Same code as local — confirm ElastiCache connection |
| PERF-03 | Configure Elastic Beanstalk auto-scaling: target 70% CPU, min 1 instance, max 4 instances | 0.5d | DevOps |  |
| PERF-04 | Load test using k6 or Artillery: AI move endpoint, Socket.io room concurrency, leaderboard queries | 1.5d | DevOps/Backend | Target: hundreds of concurrent users; AI endpoint ≤500ms |
| PERF-05 | Resolve any bottlenecks identified during load testing | 1d | Backend | Time-boxed to 1 day; defer non-critical items post-launch |

### 5.2.5 Production Go-Live

| ID | Task | Effort | Owner | Notes |
| --- | --- | --- | --- | --- |
| OPS-18 | Production readiness checklist: security review (HTTPS, CORS, rate limiting, Secrets Manager), all tests green, monitoring active | 1d | All | Sign-off required from all team members |
| OPS-19 | Deploy to production | 0.5d | DevOps |  |
| OPS-20 | Post-deploy smoke test: play a PvAI game, create a PvP room, verify auth flows, check CloudWatch logs | 0.5d | All |  |
| OPS-21 | Monitor production for 48 hours post-launch: error rates, latency, socket connections | — | All | Ongoing watch period — not a task with a fixed end |

## 5.3 v3 Summary

| Area | Tasks | Est. effort | Test coverage |
| --- | --- | --- | --- |
| AWS infrastructure provisioning | 8 | 6d | Manual smoke test |
| CI/CD pipelines | 4 | 3d | Automated (all existing tests) |
| Staging deployment & E2E re-validation | 5 | 3.5d | Full E2E suite (Playwright) |
| Performance & scalability hardening | 5 | 4d | Load test (k6/Artillery) |
| Production go-live | 4 | 2d | Smoke test + monitoring |
| Total (v3) | 26 | ~18.5 dev-days | E2E + load test + smoke |

v3 is intentionally lean — approximately 2–3 weeks. The bulk of the work was done in v1 and v2. The only new code is environment configuration switches (log destination, Clerk/Stripe production keys). Everything else is infrastructure provisioning, pipeline wiring, and validation.

# 7. Total Effort Summary

| Phase | Tasks | Est. effort | Team weeks* | Key deliverable |
| --- | --- | --- | --- | --- |
| Phase 0 — Machine prep | 26 | ~2–3d per dev | 0.5 weeks | Clean machines, tools installed, Git configured, credentials distributed |
| Prerequisites | 10 | ~7d | 1–1.5 weeks | Local stack running, project scaffolded |
| v1 — Local Foundation | 51 | ~41.5d | 4–5 weeks | Fully playable PvAI game, auth, stats — local only |
| v2 — PvP & Full Feature Set | 65 | ~69d | 8–10 weeks | PvP, real-time, all admin + monetisation — local only |
| v3 — Cloud & Go-Live | 26 | ~18.5d | 2–3 weeks | AWS deployment, load test, production go-live |
| Total | 178 | ~138d+ | 16–20 weeks | Full product delivered across 4 phases |

* Team weeks based on a 2-developer team working in parallel. The Orchestrator role adds approximately 15–20% overhead to one developer's time across all phases — this is accounted for in the estimates. 3–4 developers would reduce wall-clock time by 20–35% depending on task parallelisability. Estimates are indicative and assume focused development with minimal context-switching.

# 8. Build Sequence & Key Dependencies

The following dependency chain must be respected. Work that can be parallelised is noted.

## 7.1 Hard Dependencies (must be sequential)

- Phase 0 complete (all developer machines signed off by Orchestrator) → Prerequisites can begin

- Prerequisites complete → v1 can begin

- Database schema (DB-01–03) → all backend API tasks depend on it

- Auth (AUTH-01–05) → all protected API endpoints depend on JWT middleware

- AI service (AI-01–06) → game board AI integration depends on it

- v1 all tests green + full local stack verified → v2 can begin

- Socket.io + Redis (RT-01) → all real-time PvP tasks depend on it

- AI dashboard data collection (AID-01–03) → all AI dashboard API + frontend tasks depend on it

- v2 all tests green + full local stack verified (including E2E) → v3 can begin

- AWS infrastructure (OPS-01–08) → staging deployment and E2E re-validation depend on it

- Staging E2E pass (OPS-15–17) → production deployment (OPS-19) is blocked until staging is signed off

## 7.2 Parallel Workstreams

- Throughout v1: frontend developer works on app shell, mode selection, game board UI; backend developer works on database, auth, and AI service simultaneously.

- Throughout v2: frontend developer builds room creation/join, PvP board, and AI dashboard UI; backend developer builds Socket.io, rooms API, and AI dashboard API simultaneously.

- Throughout v2: monetisation frontend and notifications frontend can be developed in parallel with their backend counterparts once the relevant schemas are in place.

- Throughout v3: AWS infrastructure provisioning (OPS-01–08) and CI/CD pipeline setup (OPS-09–12) can proceed in parallel. Load testing (PERF-04) begins once staging is deployed.

# 9. Risks & Mitigations

| # | Risk | Prob. | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | Clerk or Apple OAuth configuration delays — Apple's developer account setup is often slow | Medium | Medium | Start AUTH-01 early in v1. Allocate 2–3 days buffer for Apple OAuth approval process. |
| R-02 | Socket.io Redis adapter introduces latency or connection instability under load | Low | High | Redis adapter included from day one (RT-01) and exercised locally throughout v2. Load tested in v3 on AWS before production go-live. |
| R-03 | AWS setup complexity delays v3 production deployment | Medium | Medium | AWS work is isolated to v3, so delays do not impact v1 or v2 development. Begin OPS-01 on day 1 of v3. |
| R-04 | Minimax Hard AI responds close to or over the 500ms threshold on complex board states | Low | Medium | Performance assertion in AI-05. If threshold is hit, cache Minimax results for symmetric board states. |
| R-05 | Stripe integration complexity delays v3 monetisation | Medium | Low | Use Stripe's hosted checkout flow (minimal custom code). Stripe test mode available from day one. |
| R-06 | AI dashboard database queries are slow at scale without proper indexing | Medium | Medium | PERF-01 adds required indexes early in v3. Redis caching on all dashboard endpoints (AID-05+). |
| R-07 | Mountain name pool exhausted under heavy concurrent room creation load | Low | Low | Pool of 1,000+ names handles hundreds of concurrent rooms. Names returned to pool on room close. Monitor active room count. |
| R-08 | E2E test flakiness (Socket.io timing, OAuth redirects) causes false failures | Medium | Medium | Use Playwright auto-waiting and retry logic. In v2 E2E runs against local Docker stack — no network variability. In v3, tag critical-path tests to block production; run full suite nightly on staging. |

# 10. Testing Checkpoints

Testing is embedded in every task, not a separate phase. The following checkpoints summarise when each testing layer is active.

| Layer | When written | When run | Scope |
| --- | --- | --- | --- |
| Unit | Alongside every task (definition of done) | On every git commit (Husky) + every push (CI) | Functions, components, AI logic, API handlers, log transport |
| Integration | When a new integration point is introduced | Every pull request (after unit tests pass) | API + DB, AI registry routing, Socket.io room lifecycle, auth middleware |
| E2E — critical path | v2 (E2E-01–02): PvAI flow, PvP flow, spectator flow | v2: locally against Docker stack. v3: every staging deploy; blocks production on failure | Full user journeys through the browser |
| E2E — full suite | v2 (E2E-03–07) + re-validated in v3 (OPS-15) | v2: locally (nightly). v3: against staging (nightly); full run before production sign-off | All screens, all flows, all three browsers (Chromium, Firefox, WebKit) |
| Load test | v3 (PERF-04) — after staging deployment | Once in v3 on AWS staging; re-run after PERF-05 fixes | AI move endpoint, Socket.io rooms at target concurrent user scale |

# 12. Orchestrator Master Checklist

This checklist is the Orchestrator's running record of progress. Every task in the development plan is listed by phase. The Orchestrator marks each item Done (✓) when the developer confirms completion, and Tested (✓) when the associated test(s) are passing and verified. No task moves to Done without a test confirmation where applicable.

Print this section or maintain it as a live document. The Orchestrator updates it during or immediately after each daily sync. A task is not closed until both columns are checked.

| ID | Task | Done | Tested |
| --- | --- | --- | --- |
| Phase 0 — Machine Preparation |
| Docker cleanup |
| M-01 | Stop and remove orphaned Docker containers | □ | □ |
| M-02 | Prune orphaned Docker volumes | □ | □ |
| M-03 | Prune unused Docker networks | □ | □ |
| M-04 | Docker Desktop updated to ≥ 4.25 | □ | □ |
| M-05 | No port conflicts on 5173, 3000, 5432, 6379 — verified per developer | □ | □ |
| Database cleanup |
| M-06 | Local Postgres instances removed or isolated (no conflict on port 5432) | □ | □ |
| M-07 | Local Redis instances removed or isolated (no conflict on port 6379) | □ | □ |
| M-08 | No residual database data directories conflicting with Docker volumes | □ | □ |
| Tool installation & verification |
| M-09 | Node.js 20 LTS installed via nvm — node --version confirmed | □ | □ |
| M-10 | npm updated to latest | □ | □ |
| M-11 | Git ≥ 2.40 installed; git config user.name and user.email set | □ | □ |
| M-12 | VS Code installed with project extensions (.vscode/extensions.json) | □ | □ |
| M-13 | Playwright system dependencies installed (npx playwright install --with-deps) | □ | □ |
| M-14 | k6 installed (brew install k6) | □ | □ |
| Git & repository setup |
| M-15 | SSH key generated and added to GitHub — ssh -T git@github.com confirmed | □ | □ |
| M-16 | GitHub repository created; main and staging branches protected (Orchestrator) | □ | □ |
| M-17 | All developers cloned repo and verified push access | □ | □ |
| M-18 | Commit signing configured (optional) | □ | □ |
| Accounts & credentials |
| M-19 | Clerk development application created; dev API keys distributed securely | □ | □ |
| M-20 | Stripe test account created; test keys distributed securely | □ | □ |
| M-21 | AWS CLI installed; aws sts get-caller-identity confirmed per developer | □ | □ |
| M-22 | All env vars documented in password manager; .env.example committed to repo | □ | □ |
| Orchestrator context infrastructure |
| M-23 | Living context document created and shared with team | □ | □ |
| M-24 | Project comms channels created (#general, #frontend, #backend, #devops, #blockers) | □ | □ |
| M-25 | Daily sync scheduled; all developers confirmed attendance | □ | □ |
| M-26 | Phase 0 sign-off checklist collected from all developers — Phase 0 closed | □ | □ |
| Prerequisites & Scaffolding |
| Repository & project structure |
| P-01 | Git monorepo structure created: /frontend, /backend, /shared | □ | □ |
| P-02 | GitHub Actions CI skeleton: lint + test on every push | □ | □ |
| P-03 | Husky pre-commit hook configured and blocking on test failure | □ | □ |
| Local development environment |
| P-04 | docker-compose.yml authored: frontend, backend, Postgres, Redis | □ | □ |
| P-05 | .env.example committed with all required keys documented | □ | □ |
| P-06 | Full local stack verified: docker compose up → all services healthy | □ | □ |
| Tooling & configuration |
| P-07 | Frontend initialised: Vite + React 18 + TypeScript + Tailwind + design tokens | □ | □ |
| P-08 | Backend initialised: Node.js 20 + Express + TypeScript + Prisma + ESLint + Prettier | □ | □ |
| P-09 | Vitest configured for frontend (React Testing Library) and backend (Supertest) | □ | □ |
| P-10 | Shared TypeScript types package (/shared) set up and consumed by both sides | □ | □ |
| v1 — Local-First Foundation |
| Database schema |
| DB-01 | Prisma schema defined: Users, Games, Moves, AI Errors, Stats tables | □ | □ |
| DB-02 | Initial Prisma migration run on local Postgres | □ | □ |
| DB-03 | Seed script created with sample users and game data | □ | □ |
| Authentication |
| AUTH-01 | Clerk development instance configured; Google and Apple OAuth set up | □ | □ |
| AUTH-02 | Clerk frontend SDK integrated: sign-in, sign-up, user button | □ | □ |
| AUTH-03 | Clerk JWT verification middleware added to Express (all protected routes) | □ | □ |
| AUTH-04 | Guest mode implemented: unauthenticated users access PvAI only | □ | □ |
| AUTH-05 | Unit tests: JWT middleware, guest access enforcement — passing | □ | □ |
| AI service |
| AI-01 | AI implementation registry module built with common interface | □ | □ |
| AI-02 | Minimax engine implemented: Easy, Medium, Hard | □ | □ |
| AI-03 | GET /api/v1/ai/implementations endpoint operational | □ | □ |
| AI-04 | POST /api/v1/ai/move endpoint operational | □ | □ |
| AI-05 | Unit tests: Minimax correctness fixtures, all difficulty behaviours, performance assertion — passing | □ | □ |
| AI-06 | Integration tests: POST /api/v1/ai/move round-trip — passing | □ | □ |
| Core API endpoints |
| API-01 | POST /api/v1/users — create user on first Clerk login | □ | □ |
| API-02 | GET/PATCH /api/v1/users/:id — fetch and update profile | □ | □ |
| API-03 | POST /api/v1/games — create game record | □ | □ |
| API-04 | PATCH /api/v1/games/:id — update on completion | □ | □ |
| API-05 | GET /api/v1/users/:id/stats — return stats | □ | □ |
| API-06 | POST /api/v1/logs — frontend log ingestion | □ | □ |
| API-07 | Integration tests for all v1 endpoints — passing | □ | □ |
| Frontend — app shell & navigation |
| FE-01 | App shell built: top nav, sidebar, mobile bottom tab nav, responsive breakpoint | □ | □ |
| FE-02 | Theme toggle implemented: light/dark/system with account persistence | □ | □ |
| FE-03 | Zustand stores set up: auth, preferences, active game | □ | □ |
| FE-04 | Component unit tests: shell, nav, theme toggle — passing | □ | □ |
| Frontend — mode selection |
| FE-05 | Mode selection screen built: PvP/PvAI cards, first-player pills, name fields, CTA | □ | □ |
| FE-06 | AI implementation selector built: fetches from /api/v1/ai/implementations | □ | □ |
| FE-07 | Unit tests: mode card selection, AI selector, CTA adaptation — passing | □ | □ |
| Frontend — game board (PvAI) |
| FE-08 | 3×3 board component built: marks, hover, win highlight | □ | □ |
| FE-09 | Game state logic: turn management, win/draw detection, board locking | □ | □ |
| FE-10 | AI move API integrated: board dims + spinner during request | □ | □ |
| FE-11 | Turn indicator, score strip, action buttons (Rematch/New Game/Forfeit) built | □ | □ |
| FE-12 | Howler.js integrated: move, win, draw, forfeit sounds + mute toggle | □ | □ |
| FE-13 | Game result persisted via POST/PATCH /api/v1/games on game end | □ | □ |
| FE-14 | Unit tests: win/draw detection, turn logic, board locking, score persistence — passing | □ | □ |
| Frontend — account & settings |
| FE-15 | Account/profile screen built: profile header, stats grid, win rate bars, streak grid, recent games | □ | □ |
| FE-16 | Settings screen built: theme, sound toggles, volume slider | □ | □ |
| FE-17 | Settings sub-sections: AI selector, account management (edit, sign out, delete) | □ | □ |
| FE-18 | Unit tests: settings persistence, profile edit, stat display — passing | □ | □ |
| Frontend — log transport |
| FE-19 | Frontend log transport built: batching, 5s dispatch, immediate ERROR/FATAL | □ | □ |
| FE-20 | Unit tests: batching logic, retry, immediate dispatch — passing | □ | □ |
| v2 — PvP, Real-Time & Full Feature Set |
| Real-time infrastructure |
| RT-01 | Socket.io added to Express with Redis adapter (local Docker Redis) | □ | □ |
| RT-02 | Room lifecycle implemented: create, join, spectate, close; mountain name assignment | □ | □ |
| RT-03 | Socket.io events implemented: move, turn, game end, forfeit, disconnect, spectator join/leave | □ | □ |
| RT-04 | 60-second reconnection window implemented | □ | □ |
| RT-05 | Spectator role enforced server-side: move/forfeit/rematch blocked | □ | □ |
| RT-06 | Integration tests: room lifecycle, reconnection, spectator enforcement — passing | □ | □ |
| Rooms API |
| API-08 | POST /api/v1/rooms — create room, assign mountain name, return invite URL | □ | □ |
| API-09 | GET /api/v1/rooms/:name — look up room by mountain name | □ | □ |
| API-10 | GET /api/v1/rooms — list active rooms (join/watch) | □ | □ |
| API-11 | Integration tests for room API endpoints — passing | □ | □ |
| Frontend — room creation & join |
| FE-21 | Room creation screen built: settings, room name preview, invite link | □ | □ |
| FE-22 | Waiting state screen built: player slots, spectator count, cancel room | □ | □ |
| FE-23 | Active rooms list built (desktop): join and watch buttons | □ | □ |
| FE-24 | Unit tests: room creation, waiting state, active rooms — passing | □ | □ |
| Frontend — PvP game board |
| FE-25 | PvP game board: Socket.io room connection, send/receive move events | □ | □ |
| FE-26 | Spectator view built: amber banner, read-only board, leave/start own game | □ | □ |
| FE-27 | Spectator list in right panel (desktop): names + join times, live count | □ | □ |
| FE-28 | Disconnection UX: notify player, countdown timer for reconnect window | □ | □ |
| FE-29 | Unit tests: PvP turn enforcement, spectator events, disconnect — passing | □ | □ |
| Leaderboard & history |
| API-12 | GET /api/v1/leaderboard — rankings with filters, paginated | □ | □ |
| API-13 | GET /api/v1/users/:id/games — game history with pagination | □ | □ |
| FE-30 | Leaderboard screen built: podium, my rank callout, filterable table | □ | □ |
| FE-31 | Game history screen built: full list, desktop only | □ | □ |
| FE-32 | Unit + integration tests: leaderboard ranking, history pagination — passing | □ | □ |
| Log viewer |
| LOG-01 | GET /api/v1/logs endpoint with filters, paginated, admin role enforced | □ | □ |
| LOG-02 | WebSocket channel for live log tail implemented | □ | □ |
| LOG-03 | Log viewer screen built: filter panel, expandable rows, live tail, export | □ | □ |
| LOG-04 | Unit + integration tests: filter logic, pagination, role enforcement — passing | □ | □ |
| E2E test suite (local) |
| E2E-01 | Playwright project set up; targets local Docker stack (localhost:5173) | □ | □ |
| E2E-02 | Critical path E2E: PvAI flow, PvP flow (two browsers), spectator flow — passing | □ | □ |
| E2E-03 | E2E: registration (email + Google + Apple OAuth), login, account stats — passing | □ | □ |
| E2E-04 | E2E: room creation, invite link, join, mountain name, active rooms — passing | □ | □ |
| E2E-05 | E2E: log viewer filter interactions, live tail, export — passing | □ | □ |
| E2E-06 | E2E: AI dashboard filter interactions, chart rendering, CSV export — passing | □ | □ |
| E2E-07 | E2E: cosmetic shop browse/purchase (mock payment), notifications — passing | □ | □ |
| AI dashboard |
| AID-01 | Prisma schema extended: Moves table | □ | □ |
| AID-02 | Prisma schema extended: AI Errors table | □ | □ |
| AID-03 | AI move endpoint updated to write per-move and error records | □ | □ |
| AID-04 | GET /api/v1/admin/ai/summary — KPI scorecard (Redis-cached) | □ | □ |
| AID-05 | GET /api/v1/admin/ai/outcomes — outcomes by difficulty | □ | □ |
| AID-06 | GET /api/v1/admin/ai/move-times — histogram (p50/p90/p99) | □ | □ |
| AID-07 | GET /api/v1/admin/ai/win-rate-trend — daily trend with deployment markers | □ | □ |
| AID-08 | GET /api/v1/admin/ai/heatmap — player move frequency data | □ | □ |
| AID-09 | GET /api/v1/admin/ai/comparison — implementation comparison | □ | □ |
| AID-10 | Socket.io channel: live AI metrics streaming to dashboard | □ | □ |
| AID-11 | Unit + integration tests: all AI dashboard endpoints — passing | □ | □ |
| AID-12 | AI dashboard shell built: filters, live indicator, auto-refresh | □ | □ |
| AID-13 | KPI scorecard row built (6 cards with deltas) | □ | □ |
| AID-14 | Outcomes by difficulty chart built (Recharts grouped bar) | □ | □ |
| AID-15 | Move time histogram built with p50/p90/p99 markers | □ | □ |
| AID-16 | Win rate over time chart built with deployment markers | □ | □ |
| AID-17 | Player opening heatmap built (3×3 colour intensity grid) | □ | □ |
| AID-18 | Implementation comparison table built | □ | □ |
| AID-19 | CSV export added to each chart panel | □ | □ |
| AID-20 | Unit tests: chart rendering, filter interactions, export — passing | □ | □ |
| Monetisation |
| MON-01 | Cosmetic item schema designed: Items and UserItems tables | □ | □ |
| MON-02 | Stripe integrated: checkout flow for purchases and subscription (test mode) | □ | □ |
| MON-03 | Cosmetic item shop frontend built: browse, purchase, apply to board | □ | □ |
| MON-04 | Premium subscription tier implemented: ad-free flag, exclusive themes | □ | □ |
| MON-05 | Non-intrusive ads implemented for guest/free-tier (outside gameplay only) | □ | □ |
| MON-06 | Unit + integration tests: purchase flow, subscription state — passing | □ | □ |
| Notifications |
| NOT-01 | Notifications schema added to Prisma | □ | □ |
| NOT-02 | In-app notification system built: opponent joined, game result, streak milestone | □ | □ |
| NOT-03 | Notifications panel built: list, mark read, clear all | □ | □ |
| NOT-04 | Email notifications implemented (opt-in) — if in scope | □ | □ |
| v3 — Cloud Deployment & Production Go-Live |
| AWS infrastructure |
| OPS-01 | AWS account structure: IAM roles, VPC, security groups, Secrets Manager | □ | □ |
| OPS-02 | RDS PostgreSQL provisioned (staging + prod); Prisma migrations run | □ | □ |
| OPS-03 | ElastiCache Redis provisioned (staging + prod) | □ | □ |
| OPS-04 | Elastic Beanstalk environments created (staging + prod) | □ | □ |
| OPS-05 | S3 bucket + CloudFront distribution set up (staging + prod) | □ | □ |
| OPS-06 | CloudWatch Logs configured; log transport env var updated for cloud | □ | □ |
| OPS-07 | Clerk production instance configured with production OAuth credentials | □ | □ |
| OPS-08 | Stripe production account and webhook endpoints configured | □ | □ |
| CI/CD pipelines |
| OPS-09 | GitHub Actions CI pipeline: lint + unit + integration on every PR | □ | □ |
| OPS-10 | GitHub Actions staging deploy pipeline built and tested | □ | □ |
| OPS-11 | GitHub Actions production deploy pipeline built (manual approval gate) | □ | □ |
| OPS-12 | CloudWatch alarms and SNS alerts configured | □ | □ |
| Staging deployment & E2E re-validation |
| OPS-13 | Full application deployed to staging environment | □ | □ |
| OPS-14 | Playwright E2E reconfigured to target staging URL | □ | □ |
| OPS-15 | Full v1 + v2 E2E suite run against staging — all passing | □ | □ |
| OPS-16 | E2E pipeline step added: critical-path tests block production promotion | □ | □ |
| OPS-17 | Staging sign-off: all features verified, all E2E green — Orchestrator sign-off | □ | □ |
| Performance & scalability hardening |
| PERF-01 | Database indexes added: Games, Moves, Users tables | □ | □ |
| PERF-02 | Redis caching verified operational in cloud: AI dashboard + leaderboard TTLs confirmed | □ | □ |
| PERF-03 | Elastic Beanstalk auto-scaling configured: 70% CPU target, 1–4 instances | □ | □ |
| PERF-04 | Load test run on staging: AI move endpoint + Socket.io rooms — targets met | □ | □ |
| PERF-05 | Load test bottlenecks resolved (if any) | □ | □ |
| Production go-live |
| OPS-18 | Production readiness checklist completed and signed off by all team members | □ | □ |
| OPS-19 | Application deployed to production | □ | □ |
| OPS-20 | Post-deploy smoke test passed: PvAI game, PvP room, auth, CloudWatch logs verified | □ | □ |
| OPS-21 | 48-hour production monitoring watch period completed | □ | □ |

# 13. Reference Documents

- Product Requirements Document (PRD) v1.0 — TicTacToe_Requirements.docx

- Technical Design Document (TDD) v1.0 — TicTacToe_TechnicalDesign.docx

- Design Document v1.0 — TicTacToe_DesignDocument.html

— End of Document —